## INV2026-01: Testing the viability of Baited Remote Underwater Video (BRUV) to monitor

trends in marine ﬁnﬁsh and biodiversity in the Fiordland Marine Area

| Project No. | INV2026-01 | Start Date | 1 September 2026 | Completion Date |  | 31 January 2028 |
| --- | --- | --- | --- | --- | --- | --- |
| Project Title | Testing the viability of Baited Remote Underwater Video (BRUV) to monitor trends in marine finfish and biodiversity in the Fiordland Marine Area |  |  |  |  |  |
| % Cost Recovered | 100% Crown Funded |  | Commercial Value |  | N/A |  |
| Cost Estimate | $175,000 |  | Contract period (Financial Years) |  | 2 year |  |

History of Project/ Stock (relevance to previous projects) In 2021 Dr. Adam Smith completed BRUV deployments on a joint research trip with the Department of Conservation (DOC) throughout the southern fiords. Seeing merit in the approach, DOC then contracted Dr Smith (as Sea Through Science Ltd) to develop a proof-of-concept survey of fish populations using BRUVs in Tamatea/Dusky Sound in 2024 and a further, more comprehensive survey focussed on Tamatea/Dusky Sound and Te Tapuwae o Hua (Wet Jacket Arm) Marine Reserve in 2025. Tamatea/Dusky Sound was proposed as an indicator area for wider Fiordland because it: 1) is the area within Fiordland that appears to have had the greatest decline in finfish from recreational fishing pressure and 2) is a valid area to test the effectiveness of recent management measures for finfish across the wider Fiordland area. DOC contracted the fieldwork element of the research to date but lack funds for video annotation and data analysis. Fisheries New Zealand fisheries managers have been in discussions with DOC and the Fiordland Marine Guardians about potential monitoring approaches to test the effectiveness of new recreational regulations in the area. There is joint interest in developing the BRUV method for both MPA and fishery monitoring. In 2024 Fisheries New Zealand contributed $50,000 towards review and annotation of the video footage collected in Dusky Sound that year (SEA2023-15). DOC have committed to continue to provide vessel time and support for field work in future BRUV surveys in Dusky Sound, but there are no funds for data analysis (of videos from 2021 and 2025 and data from 2024). Fisheries New Zealand seeks annotation and analysis of baseline data and additional field work to test whether the method is appropriate for tracking trends in blue cod between locations and over time.

Why this project/stock has been selected? Why is MPI doing this research? The Fiordland (Te Moana o Atawhenua) Marine Area’s unique marine ecosystems are managed under the Fiordland (Te Moana o Atawhenua) Marine Management Act 2005 (“the Act”) and overseen by the Fiordland Marine Guardians (“the Guardians”). The Guardians implemented new fishing regulations in 2024 which reduced mixed bag and single species limits for most species of shellfish and finfish. Past monitoring of blue cod (Parapercis colias) in Dusky Sound was infrequent and done with fishery-independent potting surveys. However, potting is now banned from the internal waters of Fiordland and developing non-invasive sampling methods is desirable to monitor key stocks. The BRUV method offers a non-destructive alternative to potting surveys for blue cod and other finfish. The Guardians have committed to reviewing the effectiveness of these management changes in future as supported by monitoring data on key fish stocks. The National Panel Survey for recreational catch is uncertain in the Fiordland region because there is a relatively low level of activity, and therefore low participation by panellists. Monitoring of blue cod in Tamatea/Dusky Sound was historically done with fishery-independent potting surveys (last done in 2014). Commercial Potting is now banned from the

internal waters of the fiords, and there are effort restrictions on recreational potting. Developing non-invasive sampling methods will be useful to monitor key stocks in this sensitive area. Fisheries New Zealand have agreed with the Guardians that this research is a priority as part of the wider Fiordland Marine Area Strategy (Fiordland Marine Guardians 2025). This work will also contribute to the development of a novel method and potential advancement for ecosystem-based fisheries management since the video data are broader than a single species approach. This is one of two projects proposed in 2026 to improve management of marine resources in Fiordland. Project MAF2026-11 will test the use of Fiordland Amateur Charter Vessel data as an index of abundance for blue cod.

How often is the research completed? This is a one-off investigation. If the results show that BRUV is a useful approach a joint monitoring plan between Fisheries New Zealand and DOC could be developed in a subsequent project.

### Overall Objective:

To analyse and report on trends in ﬁsh abundance and biodiversity from baited remote underwater videos (BRUVs) collected in Fiordland since 2021 and complete further ﬁeld work to test the power of the method for detecting trends in blue cod abundance.

### Speciﬁc Research Objectives:

- Annotate BRUVs collected in 2021 and 2025, recording data on ﬁsh abundance and length information, with a focus on blue cod and Hapuku.

- Design and implement a ﬁeld experiment to test the viability of BRUVs to detect changes in blue cod abundance.

- Analyse all BRUV data since 2021 and the results of the ﬁeld work to report on the power of the method to detect change in ﬁsh populations.

- Economic Beneﬁts to New Zealand.

### Reporting Requirements:

Research Reporting:

- To hold a project scoping meeting to discuss project goals and decision points with MPI by 15 September 2026.

- To hold an internal meeting with MPI, and DOC to discuss the methods for Objective 2 by 31 October.

- To present project methods to the Fiordland Marine Guardians (FMG), the Fisheries New Zealand Biodiversity Research Advisory Group (BRAG) and other relevant working groups by 30 November 2026.

- Submit health and safety management plan for approval 1 month before activity commences.

- To present preliminary results to the BRAG working group and other relevant working groups by 30 July 2027

- To submit to the MPI Contracts Monitoring and Administration Team, Fisheries New Zealand Science Oﬃcer, and Fisheries New Zealand project manager a draft Aquatic Environment and Biodiversity Report (AEBR) (as per Research Reporting Form 6) summarising project ﬁndings and present ﬁnal results to the BRAG working group by 31 October 2027 with a Form 9: Research Report Submission Coversheet.

- To submit a ﬁnal AEBR (as per Research Reporting Form 6) to the MPI Contracts Monitoring and Administration Team, Fisheries New Zealand Science Oﬃcer, and Fisheries New Zealand project manager by 30 November 2027 with a Form 9: Research Report Submission Coversheet.

- To submit any data generated, collected or modiﬁed during the course of this project to Fisheries New Zealand Data Management (fnzdatasubmission@mpi.govt.nz) by 30 November 2027.

Project Update Reports

No Project Update Reporting is required for this project.

Work In Progress Reports

Monthly Work In Progress Reporting is required for this project in accordance with Monthly Work In Progress Reporting is required for this project in accordance with Conducting Fisheries Research with Fisheries New Zealand. A Work In Progress Report Form 13 is to be submitted to MPI Contracts Monitoring by the ﬁfth working day of each month for the duration of the project.

Data Reporting

All data and data ﬁles upon which analyses are undertaken for this project must be provided by 30 July 2028 to Fisheries New Zealand Data Management (fnzdatasubmission@mpi.govt.nz), in the appropriate format and level of detail to allow the analysis to be repeated if required.

### Rationale:

General

The Baited Remote Underwater Video (BRUV) method oﬀers a non-destructive alternative to potting surveys for blue cod and other ﬁshed species. BRUVs are already being used by the Department of Conservation to monitor the eﬀectiveness of the national marine protected area network, and they represent the only baseline monitoring data available for Fiordland since the implementation of 2024 regulations. Literature from overseas suggests that ﬁsh traps and BRUVs can provide consistent data on relative abundance of reef ﬁsh (Bacheler et al. 2023) and BRUVs are consistently superior to traps at characterising species richness (Bacheler et al. 2022). BRUVing is an established and globally standardised method with several major advantages (Cappo et al. 2001, Campbell et al. 2015, Langlois et al. 2020) including:

- BRUV deployments can be rapidly replicated over a wide range of depths,

- they provide accurate length measures of ﬁsh,

- they can capture a broader range of species, and size-classes than destructive sampling and have the added beneﬁt of documenting associated habitats,

- a permanent video archive that can be reanalysed in perpetuity for future studies,

- this is a non-lethal approach, allowing more regular replication and earlier detection of changes,

- provides high resolution still and video imagery useful for public engagement,

- records all ﬁsh that arrive, rather than just those caught in the pot, reducing uncertainty, and

- potential to collect covariate data, for example on habitat, water clarity, current direction and strength and water temperature that can be used to standardise the time series analysis.

BRUV surveys could potentially augment or replace blue cod potting surveys in Tamatea/Dusky Sound, or more broadly. BRUVs cannot capture age structure or mortality estimation and sex ratio information and there is some uncertainty regarding how well this method can evaluate trends in abundance and size composition of blue cod. An experiment repeating both methods at a number of stations over a gradient of ﬁsh abundance to compare relative abundance and size composition in the diﬀerent strata is proposed in this project to address this question.

In addition to monitoring changes in population status for ﬁshed species, BRUVs placed inside and outside of existing marine protected areas can assess the impacts of ﬁshing on benthic and demersal biodiversity. BRUV surveys are of interest to both Fisheries New Zealand (from a ﬁsheries monitoring and ecosystem indicator perspective) and the Department of Conservation (from an MPA monitoring and ecosystem monitoring perspective). This project leverages funds between two crown agencies to support collaborative research that will address the ﬁsheries management aspirations of the Fiordland Marine Guardians and support the development of a novel monitoring approach.

This project will conduct a formal statistical analysis and report on video surveys done with support from the Department of Conservation in 2021, 2024 and 2025 (e.g., looking at the abundance and size structure of blue cod and other key species with respect to spatial patterns, habitat relationships, and interannual variation). It will also complete additional paired BRUV and potting surveys at known areas of high and low density for blue cod to assess the power to observe change in ﬁsh populations over time.

Objective 1: Annotate BRUVs collected in 2021 and 2025, recording data on ﬁsh abundance and length information, with a focus on blue cod and Hapuku

Under this objective video imagery from BRUVs collected in Fiordland in 2021 and 2025 will be annotated to collect data on ﬁsh abundance and length and general biodiversity, with special interest in blue cod and hapuku. Videos will be annotated in a comparable approach to project SEA2023-15 (Smith 2024). This includes estimates of MaxN (maximum number of each species observed in a single frame over the course of each 60-minute video) and MeanCount (average number of individuals counted across regular space time points). Length frequency data will be collected for all individuals in both MaxN and MeanCount frames.

Objective 2: Design and implement a ﬁeld experiment to test the viability of BRUVs to detect changes

in blue cod abundance

Under this objective an experimental design will be developed and implemented to compare the results of potting surveys with BRUV surveys over a gradient of blue cod abundance. The intent is to understand whether BRUVs could be used in place of potting surveys in some areas. This could be done in Dusky Sound or elsewhere, ideally in collaboration with DOC. Stereo BRUVs are increasingly being used by DOC who are currently establishing projects in Otago regarding the SEMP (South-East Marine Protection) reserves. The Otago coast may provide an ideal region for this study, with areas of high-density blue cod across depth ranges. Data collection should be consistent with the methods used for the Dusky Sound surveys. The sampling would involve simultaneous (or within the same day) deployment of BRUVs and ﬁsh pots at several reef sites with known low versus high abundances of blue cod. Historical potting surveys and diver surveys from Fiordland-wide monitoring could be referenced to help identify study sites (Beentjes & Page 2016).

Objective 3: Analyse all BRUV data since 2021 and the results of the ﬁeld work to report on the power of the method to detect change in ﬁsh populations

Under this objective, the research provider will conduct a formal statistical analysis and report on the prior Dusky surveys as well as the data collected under Objective 2. The report will analyse the variability, abundance, and size structure of blue cod and other key ﬁshed species with respect to spatial patterns (including MPA eﬀects), habitat relationships, and interannual variation. It will include an assessment of the power of the current survey design to observe change over time in comparison to potting. It will also summarise broader trends in biodiversity across sites and years (for all species observed in the videos).

This objective would also cover refinement of the survey design for key species monitored using previous results and simulation. This would include the number of spatial strata and the number of stations required in each stratum.

Objective 4: Economic Beneﬁts to New Zealand

Below is a list of likely applicable Economic Beneﬁts to address for Research Projects.. Priority economic beneﬁts the government is focused on are workforce development, workforce participation, support for NZ Businesses, local economic activity, sustainability and environmental outcomes, sustainable sourcing, innovation and capability building, social and cultural outcomes, cultural and community beneﬁts, and use of domestic resources.

Weighting of Objectives:

Weightings indicate the relative importance of each of the objectives. The weightings for the objectives in this project are (in order): 0.2, 0.4, 0.3, 0.1.

### References / Further Information:

Bacheler, N.M.; Klibansky, N.; Bubley, W.J.; Smart, T.I. (2023). Low recruitment drives the decline of red porgy (Pagrus pagrus) along the southeast USA Atlantic coast: Inferences from ﬁshery-independent trap and video monitoring. PLoS One, 18(7), p.e0286078.

Bacheler, N.M.; Zachary D.; Gillum, K.C.; Gregalis, E.P.; Pickett, C.M.; Schobernd, Z.H.; Schobernd, B.Z.; Teer, B.; Smart, T.I.; Walter, B. (2022). Comparison of video and traps for detecting reef ﬁshes and quantifying species richness in the continental shelf waters of the southeast USA. Marine Ecology Progress Series 698: 111–123.

Beentjes, M.P.; Page, M. (2016). Relative abundance, size and age structure, and stock status of blue cod in Dusky Sound, Fiordland in 2014. New Zealand Fisheries Assessment Report 2016/42.

Campbell, M.D.; Pollack, A.G.; Gledhill, C.T.; Switzer, T.S.; DeVries, D.A. (2015). Comparison of relative abundance indices calculated from two methods of generating video count data. Fisheries Research, 170: 125–133.

Cappo, M.; Speare, P.; Wassenberg, T.; Harvey, E.; Rees, M.; Heyward, A.; Pitcher, R. (2001). The use of baited remote underwater video stations (BRUVS) to survey demersal ﬁsh stocks-how deep and meaningful. In Direct sensing of the size frequency and abundance of target and non-target fauna in Australian ﬁsheries-a national workshop (pp. 63-71).

Fiordland Marine Guardians (2025). Strategic priorities 2025-28 Fiordland Marine Area. https://fmg.org.nz/sites/default/ﬁles/2025-09/FINAL%20FMA%20Strategic%20Priorities%202025-28.pdf

Langlois, T.; Goetze, J.; Bond, T.; Monk, J.; Abesamis, R.A.; Asher, J.; Barrett, N.; Bernard, A.T.; Bouchet, P.J.; Birt, M.J.; Cappo, M. (2020). A ﬁeld and video annotation guide for baited remote underwater stereo-video surveys of demersal ﬁsh assemblages. Methods in Ecology and Evolution, 11(11): 1401–1409.

Smith, A.H. (2024). Analysis of baited underwater video – Hapuku and blue cod monitoring. Short Summary Report for MPI. 10 p.

Smith, A.H. (2025). Stereo Baited Remote Underwater Video Survey of the Hauraki Gulf, 2025. Survey Sea Through Science. Report prepared for the Department of Conservation. 25 p.